## Dashboard
#VALUE! | Schedule supervision | Planned/Arrival Avg.time | 0:02 |  |  | Total Installed | 70
|  | Arrival time | 5:30 | Start date | 2025-10-22 | # sites installed | 70
Accumulated time Spent all sites [hh]:[mm]:[ss] | 132:40 | Real/Arrival Avg.time | -0.011222 | The most recent installation | 2026-04-22 | Next sites on roadmap | 0
[6 empty] | Total Quantity sites planned | 90
Average time spent per site [hh]:[mm]:[ss] | 2:39 | Start time accumulated deviation [hh]:[mm]:[ss] | 0:19 | How many calendar days transcurred | 190 | Progress | 77.78%

## Control
Status of installations completed and scheduled
Devices |  |  | Initial Schedule |  |  | Execution | [5 empty] | Site |  | Comments
Devices | Serial | Reference | Planned Date | Planned Time | Arrival time | Real Start time | End time | Duration | Early arrive | Previous date | Status | Address | Loc. Code | Notes
|  |  |  | 5:32 | 5:30 | 5:46 |  | 132:40 | -0.0013889 | [5 empty] | waiting time for site access
MX250-HW | Q3LC-527T-VHDP | Firewall | 2025-10-22 | 8:00 | 8:26 | 8:27 | 15:09 | 6:42 | -0.018056 |  | Completed | Financial Park, piso 41 | 0 | No comments
MR44-HW | Q3AL-EBTB-ANH4 | AP | 2025-10-27 | 1:00 | 0:43 | 0:45 | 3:55 | 3:10 | 0:17 |  | Completed | San Vicente, chilibre | 100 | AP not available-we did update-ports ID-ports-organizing
MR44-HW | Q3AL-XD7N-RXMU | AP | 2025-10-28 | 5:00 | 4:55 | 4:58 | 9:40 | 4:42 | 0:05 |  | Completed | Villa Lucre | P25 | No comments
MR44-HW | Q3AL-QFHA-F7MB | AP | 2025-11-01 | 5:00 | [6 empty] | Cancelled | Royal Blue Plaza | NA | Was cancelled twice, now we are watting a new date
MX67-HW | Q2FY-8J33-QYL9 | Firewall | lunes, 12 de enero de 2026 | 7:00 | 6:50 | 7:00 | 9:27 | 2:27 | 0:10 |  | Completed | Los Pueblos | P51 | No comments
MR44-HW | Q3AL-VFSD-6SPG | AP | miercoles, 14 de enero de 2026 | 4:00 | 4:25 | 4:27 | 8:37 | 4:10 | -0.017361 |  | Completed | Villa Catalina Airport Plaza | P90 | No comments
MX68-HW | Q2KY-S5FG-GAZ2 | Firewall | jueves, 15 de enero de 2026 | 4:00 | 4:13 | 4:13 | 8:47 | 4:34 | -0.0090278 |  | Completed | C.C. Plaza Las Americas/Ofibodegas Tocumen | P72 | No comments
MX67-HW | Q2FY-8HA6-3Z8N | Firewall | " | after the previous | [6 empty] | Completed | CDP - Plaza las Americas | P72K1 | No comments
MR44-HW | Q3AL-6U99-GPCZ | AP | viernes, 16 de enero de 2026 | 4:00 | 4:03 | 4:09 | 7:17 | 3:08 | -0.0020833 |  | Completed | Via España | P02 | No comments
MR44-HW | Q3AL-S54A-R6A8 | AP | lunes, 19 de enero de 2026 | 5:00 | 5:01 | 5:12 | 12:15 | 7:03 | -0.00069444 |  | Completed | CC Los Pueblos | P37 | No comments
MR36H-HW | Q3KB-HR6R-WHFS | AP | " | after the previous | [6 empty] | Completed | CDP - Los Pueblos | P37K1 | No comments
MR44-HW | Q3AL-2GZ4-VDGJ | AP | miercoles, 21 de enero de 2016 | 5:30 | 5:19 | 5:22 | 7:36 | 2:14 | 0:11 |  | Completed | La Siesta | P24 | No comments
MX67-HW | Q2FY-8GDK-TZG9 | Firewall | jueves, 22 de enero de 2026 | 6:00 | 5:59 | 6:06 | 7:23 | 1:17 | 0:01 |  | Completed | Agora Chanis | P27 | No comments
MX67-HW | Q2FY-8JQA-G6KE | Firewall | viernes, 23 de enero de 2026 | 8:00 | 7:04 | 7:45 | 9:54 | 2:09 | 0:56 |  | Completed | Metromall | P59 | No comments
MX68-HW | Q2KY-S7L9-YJMR | Firewall | " | after the previous | [6 empty] | Completed | CDP - Metromall | P59K1 | No comments
MR44-HW | Q3AL-TW7V-8GXE | AP | lunes, 26 de enero de 2026 | 5:00 | 5:06 | 5:16 | 12:25 | 7:09 | -0.0041667 |  | Completed | La Doña | P44 | La hora de inicio fue cambiada de la 5am para las 7am
MX68-HW | Q2KY-S4PC-G58N | Firewall | " | after the previous | [6 empty] | Completed | CDP - Terminal de transporte La Doña | P44K1 | No comments
MX68-HW | Q2KY-S3Y3-R59J | Firewall | " | after the previous | [6 empty] | Completed | CDP - Centro comercial Super Xtra | P44K2 | No comments
MR44-HW | Q3AL-2VWX-JGQM | AP | martes, 27 de enero de 2026 | 5:00 | 5:05 | 5:07 | 14:32 | 9:25 | -0.0034722 |  | Completed | El Parador | P10 | No comments
MR36H-HW | Q3KB-A6SM-3D3N | AP | " | after the previous | [6 empty] | Completed | CDP - Super Xtra Las Acacias | P10K1 | No comments
MR44-HW | Omited | AP | lunes, 02 de febrero de 2026 | 7:00 | 7:05 | 7:18 | 11:14 | 3:56 | -0.0034722 |  | Completed | Altaplaza Mall | P33 | No comments
MR36-HW | Q3KB-KN95-ABMP | AP | " | after the previous | [6 empty] | Completed | CDP - Alta Plaza | P33K1 | No comments
MR44-HW | Q3AL-UD79-BZAP | AP | martes, 03 de febrero de 2026 | 5:00 | 5:22 | 5:26 | 6:16 | 0:50 | -0.015278 |  | Completed | Plaza Centennial | P52 | No comments
MR44-HW | Q3AL-TVLS-VAW8 | AP | miercoles, 04 de febrero de 2026 | 5:00 | 4:59 | 5:17 | 6:31 | 1:14 | 0:01 |  | Completed | Av. Ernesto T. Lefevre y Calle 82 Este | P86 | No comments
MR44-HW | Q3AL-GKUS-Y8ZZ | AP | jueves, 05 de febrero de 2026 | 5:00 | 5:11 | 5:52 | 6:49 | 0:57 | -0.0076389 |  | Completed | Via Cincuentenario Esq. Av. 4 C Sur | P68 | No comments
MR44-HW | Q3AL-NCMM-7FKC | AP | viernes, 06 de febrero de 2026 | 5:00 | 5:37 | 5:45 | 6:34 | 0:49 | -0.025694 |  | Completed | Plaza Versalles | P63 | No comments
MR44-HW | Q3AL-XUEQ-X8KC | AP | lunes, 09 de febrero de 2026 | 5:00 | 5:04 | 5:59 | 6:35 | 0:36 | -0.0027778 |  | Completed | Transístmica con Vía Brasil, | P11 | No comments
MR44-HW | Q3AL-AEZ8-Y3UR | AP | martes, 10 de febrero de 2026 | 5:00 | 5:06 | 5:58 | 7:08 | 1:10 | -0.0041667 |  | Completed | Calle 50 | P04 | No comments
MR44-HW | Q3AL-5JTA-YMUT | AP | miercoles, 11 de febrero de 2026 | 5:30 | 5:33 | 5:35 | 6:26 | 0:51 | -0.0020833 |  | Completed | Ave. Balboa | P09 | No comments
MX67-HW | Q2FY-8GLS-D4VY | AP | jueves, 12 de febrero de 2026 | 8:00 | 8:32 | 8:45 | 9:39 | 0:54 | -0.022222 |  | Completed | Town Center | P99 | No comments
MR44-HW | Q3AL-WHKB-7N83 | AP | viernes, 13 de febrero de 2026 | 5:00 | 5:13 | 5:24 | 6:15 | 0:51 | -0.0090278 |  | Completed | Antiguas Vías del Ferrocarril | P12 | No comments
NA | NA | NA | lunes, 16 de febrero de 2026 | NA | [6 empty] | NA | NA | NA | No comments
NA | NA | NA | martes, 17 de febrero de 2026 | NA | [6 empty] | NA | NA | NA | No comments
NA | NA | NA | miercoles, 18 de febrero de 2026 | NA | [6 empty] | NA | NA | NA | No comments
MR44-HW | Q3AL-TNG5-4WUY | AP | jueves, 19 de febrero de 2026 | 8:00 | 7:39 | 8:04 | 11:28 | 3:24 | 0:21 |  | Completed | Plaza Comercial Villa Lobos | P28 | No comments
MR44-HW | Q3AL-JDXA-7ZKY | AP | viernes, 20 de febrero de 2026 | 5:00 | 4:54 | 5:03 | 6:29 | 1:26 | 0:06 |  | Completed | Vía España (Hospital San Fernando) | P08 | No comments
MR44-HW | Q3AL-G3XT-R2DT | AP | lunes, 23 de febrero de 2026 | 4:00 | 3:58 | 4:05 | 5:27 | 1:22 | 0:02 |  | Completed | Ave. Justo Arosemena /Calle 34 Este | P98 | No comments
MR44-HW | Q3AL-C3EN-AHH3 | AP | martes, 24 de febrero de 2026 | 5:00 | 4:50 | 5:05 | 6:36 | 1:31 | 0:10 |  | Completed | Vacamonte | P73 | No comments
MR44-HW | Q3AL-XNXK-B6JP | AP | miercoles, 25 de febrero de 2026 | 5:00 | 4:52 | 5:09 | 9:00 | 3:51 | 0:08 |  | Completed | La Espiga | P71 | No comments
MR36-HW | Q3KB-EF39-R7ZG | AP | " | after the previous | [6 empty] | Completed | CDP - La Espiga | P71K2 | No comments
MR44-HW | Q3AL-6D6J-FVAM | AP | jueves, 26 de febrero de 2026 | 5:00 | 4:59 | 5:18 | 9:22 | 4:04 | 0:01 |  | Completed | Centro Comerial La Marquesa | P29 | No comments
MR44-HW | Q3AL-ABK9-RDZZ | AP | viernes, 27 de febrero de 2026 | 5:00 | 5:12 | 5:16 | 7:19 | 2:03 | -0.0083333 |  | Completed | Coronado Mall | P57 | No comments
NA | NA | NA | " | after the previous | [6 empty] | Cancelled | CDP - Coronado | P57K1 | CDP not available the internet service
MR44-HW | Q3AL-VFEW-6YK6 | AP | 2026-03-02 | 5:00 | 5:04 | 5:09 | 7:15 | 2:06 | -0.0027778 |  | Completed | Penonome | P62 | No comments
MR36-HW | Q3KB-D3RC-ZQB6 | AP | 2026-03-02 | after the previous | [6 empty] | Completed | CDP - Penonome | P62K1 | No comments
TBD | TBD | AP | 2026-03-04 | 5:00 | 5:00 | 5:45 | 9:28 | 3:43 | 0:00 |  | Completed | La Cabima | P76 | 45 min delayed watting the restaurant manager
MR68-HW | Q2KY-S79U-WBSL | AP | 2026-03-04 | after the previous | [6 empty] | Completed | CDP - La Cabima minimall | P76K1 | No comments
MR68-HW | Q2KY-RY98-B32P | AP | 2026-03-04 | after the previous | [6 empty] | Completed | CDP - La Cabima, Carr Transistmica | P76K2 | No comments
MR44-HW | Q3AL-8PTY-XDN6 | AP | 2026-03-06 | 5:00 | 5:00 | 5:48 | 7:30 | 1:42 | 0:00 |  | Completed | Calidonia frente a local Pantera Rosa | P34 | 50 min delayed watting the restaurant manager
MR44-HW | Q3AL-33Q5-PHRZ | AP | 2026-03-09 | 5:30 | 5:34 | 5:38 | 7:20 | 1:42 | -0.0027778 |  | Completed | Penonome Este | P13 | No comments
MR36-HW | Q3KB-HQY4-KZL9 | AP | 2026-03-09 | after the previous | [6 empty] | Completed | CDP - Penonome plaza los Naranjos | P13K1 | No comments
MR44-HW | Q3AL-YHRX-U7GK | AP | 2026-03-11 | 5:30 | 5:39 | 6:09 | 6:57 | 0:48 | -0.00625 |  | Completed | Estacionamientos de Albrook Mall | P17 | No comments
MX67-HW | Q2FY-8GZX-QR8Y | AP | 2026-03-13 | 9:30 | 9:07 | 9:17 | 10:03 | 0:46 | 0:23 |  | Completed | Las Anclas Mall | P92 | No comments
MR44-HW | (Q3AL-AF64-ZNN8) | AP | 2026-03-16 | 5:00 | 5:02 | 5:29 | 6:50 | 1:21 | -0.0013889 |  | Completed | Villa Zaita Edificio P.H. Plaza Zaita | P106 | No comments
MX67-HW | (TBC) | AP | 2026-03-18 | 5:00 | 4:54 | 5:36 | 7:00 | 1:24 | 0:06 |  | Completed | Albrook mall, Terminal de Transporte | P39 | Start delayed because no access to parking lot
MR44-HW | Q3AL-PP5U-H8W2 | AP | 2026-03-20 | 5:00 | 4:50 | 5:03 | 6:45 | 1:42 | 0:10 |  | Completed | Plaza La Mitra, La Chorrera | P07 | No comments
MR44-HW | Q3AL-CBZ4-YVEK | AP | 2026-03-23 | 5:30 | 5:38 | 5:51 | 7:25 | 1:34 | -0.0055556 |  | Completed | Ctro Comercial El Paso Plaza Aguadulce | P21 | 13 min delayed watting the restaurant manager
MR44 | Q3AL-ZQP2-K5DZ | AP | 2026-03-25 | 5:00 | 5:48 | 5:50 | 6:26 | 0:36 | -0.033333 |  | Completed | Las Arcadas del Hotel El Panamá | P06 | No comments
NA | NA | AP | 2026-03-25 | 4:30 | [6 empty] | Cancelled | CDP - Las Arcadas del Hotel El Panamá | P06K1 | No comments
MR44 | Q3AL-VU6T-95LD | AP | 2026-03-27 | 5:30 | 5:30 | 5:58 | 6:48 | 0:50 | 0:00 |  | Completed | Peatonal, Ave Central | P47 | 15 min delayed watting the restaurant manager
MR44 | Q3AL-SRC9-9E7C | AP | 2026-03-30 | 5:30 | 5:30 | 5:51 | 10:06 | 4:15 | 0:00 |  | Completed | Ctro Comercial Costa Verde | P79
NA | NA | AP | 2026-03-31 | 5:30 | [6 empty] | Cancelled | Mañanitas | P95
MR44-HW | Q3AL-QFHA-F7MB | AP | 2026-04-06 | 5:00 | 5:05 | 5:17 | 6:56 | 1:39 | -0.0034722 |  | Completed | Av. Dr. Belisario Porras 4802 | P112
MR44 | Q3AL-9QC5-BCUH | AP | 2026-04-08 | 5:00 | [6 empty] | Cancelled | Centro Comercal Mis Provincias | P19
MR36 | Q3KB-TMES-6NDP | AP | 2026-04-08 | 5:00 | [6 empty] | Cancelled | Supermecardo El Fuerte Villa Zaita | P19K2
MR36 | Q3KB-5HSH-X2VN | AP | 2026-04-08 | 5:00 | [6 empty] | Cancelled | Plaza Comercial San Isidro | P19K3
TBD | TBD | AP | 2026-04-10 | 8:00 | 8:07 | 8:21 | 12:50 | 4:29 | -0.0048611 |  | Completed | Megamall, Foodcourt local L14 y L15 | P83 | Not recieved by formal ticket from email (Device TBD)
TBD | TBD | AP | 2026-04-10 | 8:00 | [6 empty] | Completed | Megamall, frente al Costo | P83K3 | Not recieved by formal ticket from email (Device TBD)
TBD | TBD | AP | 2026-04-10 | 8:00 | [6 empty] | Completed | Megamall, Super 99 | P83K2 | Not recieved by formal ticket from email (Device TBD)
TBD | TBD | AP | 2026-04-10 | 8:00 | [6 empty] | Completed | Megamall, frente a Madison y Oca Loca | P83K1 | Not recieved by formal ticket from email (Device TBD)
MR44 | Q3AL-TV9N-J4EG | AP | 2026-04-13 | 5:00 | 4:59 | 5:06 | 9:24 | 4:18 | 0:01 |  | Completed | El Bosque, calle las Palmeras | P22
MR36 | Q3KB-NK2E-62DK | AP | 2026-04-13 | 5:00 | [6 empty] | Completed | Dentro de la Gran Estación Linea 1 | P22K3
MR36 | Q3KB-VTDL-WVHR | AP | 2026-04-13 | 5:00 | [6 empty] | Completed | Frente al Supermercado El Fuerte, Monte Oscuro | P22K2
MR36 | Q3KB-AMLJ-8Y8V | AP | 2026-04-13 | 5:00 | [6 empty] | Completed | Super Xtra de Pan de Azucar, Centro Comercial Oriental | P22K1
MR44 | Q3AL-UNUZ-CBPA | AP | 2026-04-15 | 4:30 | 4:22 | 4:32 | 7:08 | 2:36 | 0:08 |  | Completed | Marbella | 101
MR44 | Q3AL-QEJZ-9B4R | AP | 2026-04-17 | 5:30 | 5:15 | 5:37 | 8:08 | 2:31 | 0:15 |  | Completed | Estacionamientos del Centro Comercial Westland Mall | P70
MX68 | Q2KY-S74T-WPQH | AP | 2026-04-20 | 5:00 | 5:04 | 5:10 | 7:16 | 2:06 | -0.0027778 | 2026-04-01 | Completed | Borde Centro Comercial Megamall | P20
TBD | TBD | AP | 2026-04-20 | 5:00 | [6 empty] | Cancelled | Pacora Montemadero | 104
MX67 | Q2FY-A3WB-8RV7 | AP | 2026-04-22 | 8:00 | 7:57 | 8:35 | 13:08 | 4:33 | 0:03 |  | Completed | Los Andes mall, Local 030 | P67
MR36 | Q3KB-QTBM-ZHY5 | AP | 2026-04-22 | 8:00 | [6 empty] | Completed | Los Andes Mall, Piso 2 | P67K2
MR36 | Q3KB-DN2U-BZEU | AP | 2026-04-22 | 8:00 | [6 empty] | Completed | Los Andes Mall, Piso 1 | P67K1
TBD | TBD | AP | 2026-04-22 | 5:00 | [6 empty] | Cancelled | El Dorado | P05
TBD | TBD | AP | 2026-04-22 | 5:00 | [6 empty] | Cancelled | EL Dorado Mall | P05K1
TBD | TBD | AP | 2026-04-24 | 5:30 | [6 empty] | Cancelled | Westland Mall, Foodcourt Local PA-N1 | P66
TBD | TBD | AP | 2026-04-24 | 5:30 | [6 empty] | Cancelled | Westland Mall, Foodcourt Local piso 2 | P66K1
TBD | TBD | AP | 2026-04-27 | 5:00 | [6 empty] | Cancelled | Estacionamientos, Los Andes Mall | P93
TBD | TBD | AP | 2026-04-27 | 5:00 | [6 empty] | Cancelled | Frente a Popeyes, Los Andes Mall | P93K3
TBD | TBD | AP | 2026-04-27 | 5:00 | [6 empty] | Cancelled | Frente a Super 99, Los Andes Mall | P93K2
TBD | TBD | AP | 2026-04-27 | 5:00 | [6 empty] | Cancelled | Frente a entrada de Los Andes Mall | P93K1
MR36 | Q3KB-DN2U-BZEU | AP | 2026-04-29 | 5:30 | [6 empty] | Cancelled | Av. 17 de Abril, Changuinola Centro | P82
Note on N64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was omitted by Claro, and included after the notification.

## Schedule supervision
Initial Date | Initial Time | Arrival time | Start time
2025-10-22 | 8:00 | 8:26 | 8:27
2025-10-27 | 1:00 | 0:43 | 0:45
2025-10-28 | 5:00 | 4:55 | 4:58
lunes, 12 de enero de 2026 | 7:00 | 6:50 | 7:00
miercoles, 14 de enero de 2026 | 4:00 | 4:25 | 4:27
jueves, 15 de enero de 2026 | 4:00 | 4:13 | 4:13
viernes, 16 de enero de 2026 | 4:00 | 4:03 | 4:09
lunes, 19 de enero de 2026 | 5:00 | 5:01 | 5:12
miercoles, 21 de enero de 2016 | 5:30 | 5:19 | 5:22
jueves, 22 de enero de 2026 | 6:00 | 5:59 | 6:06
viernes, 23 de enero de 2026 | 8:00 | 7:04 | 7:45
lunes, 26 de enero de 2026 | 5:00 | 5:06 | 5:16
martes, 27 de enero de 2026 | 5:00 | 5:05 | 5:07
lunes, 02 de febrero de 2026 | 7:00 | 7:05 | 7:18
martes, 03 de febrero de 2026 | 5:00 | 5:22 | 5:26
miercoles, 04 de febrero de 2026 | 5:00 | 4:59 | 5:17
jueves, 05 de febrero de 2026 | 5:00 | 5:11 | 5:52
viernes, 06 de febrero de 2026 | 5:00 | 5:37 | 5:45
lunes, 09 de febrero de 2026 | 5:00 | 5:04 | 5:59
martes, 10 de febrero de 2026 | 5:00 | 5:06 | 5:58
miercoles, 11 de febrero de 2026 | 5:30 | 5:33 | 5:35
jueves, 12 de febrero de 2026 | 8:00 | 8:32 | 8:45
viernes, 13 de febrero de 2026 | 5:00 | 5:13 | 5:24
jueves, 19 de febrero de 2026 | 8:00 | 7:39 | 8:04
viernes, 20 de febrero de 2026 | 5:00 | 4:54 | 5:03
lunes, 23 de febrero de 2026 | 4:00 | 3:58 | 4:05
martes, 24 de febrero de 2026 | 5:00 | 4:50 | 5:05
miercoles, 25 de febrero de 2026 | 5:00 | 4:52 | 5:09
jueves, 26 de febrero de 2026 | 5:00 | 4:59 | 5:18
viernes, 27 de febrero de 2026 | 5:00 | 5:12 | 5:16
2026-03-02 | 5:00 | 5:04 | 5:09
2026-03-04 | 5:00 | 5:00 | 5:45
2026-03-06 | 5:00 | 5:00 | 5:48
2026-03-09 | 5:30 | 5:34 | 5:38
2026-03-11 | 5:30 | 5:39 | 6:09
2026-03-13 | 9:30 | 9:07 | 9:17
2026-03-16 | 5:00 | 5:02 | 5:29
2026-03-18 | 5:00 | 4:54 | 5:36
2026-03-20 | 5:00 | 4:50 | 5:03
2026-03-23 | 5:30 | 5:38 | 5:51
2026-03-25 | 5:00 | 5:48 | 5:50
2026-03-27 | 5:30 | 5:30 | 5:58
2026-03-30 | 5:30 | 5:30 | 5:51
2026-04-06 | 5:00 | 5:05 | 5:17
2026-04-10 | 8:00 | 8:07 | 8:21
2026-04-13 | 5:00 | 4:59 | 5:06
2026-04-15 | 4:30 | 4:22 | 4:32
2026-04-17 | 5:30 | 5:15 | 5:37
2026-04-20 | 5:00 | 5:04 | 5:10
2026-04-22 | 8:00 | 7:57 | 8:35